2020 COMPOSITE ACTION PLAN

| NO. | ACTIVITIES (OPERATIONS) |  | LOCATION | BASELINE |  | OUTPUT INDICATORS | QUARTERLY TIME SCHEDULE |  |  |  |  |  |  |  |  |  |  |  | INDICATIVE BUDGET GHS |  |  |  |  | IMPLEMENTING AGENCIES |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Q1 |  | Q2 |  |  |  | Q3 |  |  |  | Q4 |  | DACF |  |  |  | IGF | DON OR |  |  |  |  |  |  | LEAD |  | COLLABORATING |  |
| PROGRAMME: MANAGEMENT AND ADMINISTRATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUB-PROGRAMME: GENERAL ADMINISTRATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Strengthening of Sub Metro Structures |  | CCMA |  |  | Sub Metro Structures Strengthened |  |  |  |  |  |  |  |  |  |  |  |  | 71,575.99 |  |  |  |  |  |  |  |  |  |  |  | CCMA |  | CENTRAL ADM |  |
|  | Official & National Celebrations |  | CCMA |  |  | Official & National Celebrated |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 40,000.00 |  |  |  | - |  |  |  | CCMA |  | CENTRAL ADM |  |
|  | Procurement of Office Supplies & Consumables |  | CCMA |  |  | Office Supplies & Consumables Procured |  |  |  |  |  |  |  |  |  |  |  |  | 27,881.34 |  |  |  | 9700.00 |  |  |  | - |  |  |  | CCMA |  | CENTRAL ADM |  |
|  | Support Payment of School Fees for Needy Students and other Recurrent Expenses of the Two MPs |  | CCMA |  |  | Payment of School Fees for Needy Students and other Recurrent Expenses of the Two MPs Supported |  |  |  |  |  |  |  |  |  |  |  |  | 480,000.00 |  |  |  |  |  |  |  | - |  |  |  | CCMA |  | CENTRAL ADM |  |
|  | Support Community Initiative Progammes & Provision of Social Amenities for the Two MP's |  | CCMA |  |  | Community Initiative Progammes & Provision of Social Amenities for the Two MP's Supported |  |  |  |  |  |  |  |  |  |  |  |  | 320,000.00 |  |  |  |  |  |  |  | _ |  |  |  | CCMA |  | CENTRAL ADM |  |
|  | Undertake Information, Education & Communication (Adverts, Media Coverage, NACAP etc) |  | CCMA |  |  | Information, Education & Communication (Adverts, Media Coverage, NACAP etc) undertaken |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 79,000.00 |  |  |  | _ |  |  |  | CCMA |  | CENTRAL ADM |  |
|  | Protocol Services |  | CCMA |  |  | Protocol Service |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 122,000.00 |  |  |  | _ |  |  |  | CCMA |  | CENTRAL ADM |  |
|  | Support to Traditional Authorities |  | CCMA |  |  | Traditional Authorities Supported |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 44,000.00 |  |  |  |  |  |  |  | CCMA |  | CENTRAL ADM |  |
|  | Local /International Affiliations |  | CCMA |  |  | Local/International Affiliations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 25,000.00 |  |  |  |  |  |  |  | CCMA |  | CENTRAL ADM |  |
|  | Procurement of Office Equipment & Logistics (Computers, Printers, F&F) |  | CCMA |  |  | Office Equipment & Logistics (Computers, Printers, F&F) Procured |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 82,470.00 |  |  |  |  |  |  |  | CCMA |  | CENTRAL ADM |  |
| SUB-PROGRAMME PLANNING AND CO-ORDINATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Monitoring and Evaluation of development projects |  | CCMA |  |  | Projects monitored and evaluated |  |  |  |  |  |  |  |  |  |  |  |  | 45,000.00 |  |  |  |  |  |  |  |  |  |  |  | CCMA |  | CENTRAL ADM |  |
|  | Citizens Participation in Local Governance |  | CCMA |  |  | Citizens in Local Governance Participated |  |  |  |  |  |  |  |  |  |  |  |  | 25,000.00 |  |  |  | 5,000.00 |  |  |  |  |  |  |  | CCMA |  | CENTRAL ADM |  |
| JUDICIAL ADMINISTRATION LEGAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Administrative & Technical Meetings | CCMA |  |  |  | Administrative & Technical Meetings held |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 97,598.40 |  |  |  | - |  |  |  | CCMA |  | LEGAL DEPT |  |
|  | Organisation of Audit Committee Meetings | CCMA |  |  |  | Audit Committee Meetings held Organized |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 20,000.00 |  |  |  | - |  |  |  | CCMA |  | LEGAL DEPT |  |
|  | Justice Delivery & Legal Services | CCMA |  |  |  | Justice Delivery & Legal Services |  |  |  |  |  |  |  |  |  |  |  |  | 10,000.00 |  |  |  | 20,000.00 |  |  |  |  |  |  |  | CCMA |  | LEGAL DEPT |  |
| NO. | ACTIVITIES (OPERATIONS) | LOCATION |  | BASELINE |  | OUTPUT INDICATORS | QUARTERLY TIME SCHEDULE |  |  |  |  |  |  |  |  |  |  |  | INDICATIVE BUDGET GHS |  |  |  |  |  |  |  |  |  |  |  | IMPLEMENTING AGENCIES |  |  |  |
|  |  |  |  |  |  |  | Q1 |  | Q2 |  |  |  | Q3 |  |  |  | Q4 |  | DACF |  |  |  | IGF |  |  |  | DON OR |  |  |  | LEAD |  | COLLABORATING |  |
|  | Construction of Court | CCMA |  |  |  | Court Constructed |  |  |  |  |  |  |  |  |  |  |  |  | 400,000.00 |  |  |  |  |  |  |  |  |  |  |  | CCMA |  | LEGAL DEPT |  |
| HUMAN RESOURCE MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Manpower & Skills Development | CCMA |  |  |  | Manpower & Skills Developed |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 30,000.00 |  | 66,950.00 |  |  |  |  |  |  |  |  | CCMA | HR DEPT. |  |
|  | Organisation of Capacity workshop for Assembly members | CCMA |  |  |  | Capacity workshop for Assembly members organised |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 55,000.00 |  |  |  |  |  |  |  |  | CCMA | HR DEPT. |  |
| SUB-PROGRAMME: PUBLIC WORK SERVICE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Rehabilitation of the Assembly's office Block | CCMA |  |  |  | Assembly's office Block Rehabilitated |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 101,581.00 |  |  |  |  |  |  |  | _ |  |  | CCMA | MWD |  |
|  | Construction of office Block for Cape Coast North Sub Metro | Abura |  |  |  | Office Block for Cape Coast North Sub Metro Constructed |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 222,300.34 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Completion of Community Centre | Kwaprow |  |  |  | Community Centre Completed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 17,727.03 |  |  |  |  |  | _ |  |  | CCMA | MWD |  |
|  | Completion of training centre | Siwdu |  |  |  | Training centre Completed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 72,000.00 |  |  |  |  |  | _ |  |  | CCMA | MWD |  |
|  | Supervision & Regulation of development | CCMA |  |  |  | Supervision & Regulation of development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 20,000.00 |  |  |  |  |  | _ |  |  | CCMA | MWD |  |
|  | Maintenance of Residential Buildings and Official Buildings (Minor repairs) | CCMA |  |  |  | Residential Buildings and Official Building Maintained |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 5,891.05.00 |  |  |  |  |  |  |  |  | CCMA | MWD |  |
|  | Maintenance & Repairs Air conditions & Furniture & Fixtures,etc | CCMA |  |  |  | Air conditions & Furniture & Fixtures, Maintained & Repaired |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 4,000.00 |  |  |  |  |  | _ |  |  | CCMA | MWD |  |
|  | Assisting community Self Help Projects in the various communities | CCMA |  |  |  | Community Self Help Projects assisted |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 178,939.97 |  |  |  |  |  |  |  | - |  |  | CCMA | MWD |  |
|  | Completion Police Station | Abura |  |  |  | Police Station Completed |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 181,916.50 |  |  |  |  |  |  |  | - |  |  | CCMA | MWD |  |
| SUB-PROGRAMME: URBAN ROADS MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Manpower & Skills Development | Metro wide |  |  |  | Manpower & Skills Developed |  |  |  |  |  |  |  |  |  |  |  |  |  | 2,000.00 |  |  |  |  |  | _ |  |  |  |  | URBAN RAOD DEPT. |  | CCMA |  |
|  | Procurement of Office Supplies & Consumables | Metro wide |  |  |  | Office Supplies & Consumables Procured |  |  |  |  |  |  |  |  |  |  |  |  |  | 19,456.91 |  |  |  |  |  | _ |  |  |  |  | URBAN RAOD |  | CCMA |  |
|  | Construction of Drains | Kwaproe/Amamoma |  |  |  | Drains Constructed |  |  |  |  |  |  |  |  |  |  |  |  |  | _ |  |  | 111,232.92 |  |  | _ |  |  |  |  | URBAN RAOD DEPT. |  | CCMA |  |
| NO. | ACTIVITIES (OPERATIONS) | LOCATION |  | BASELINE |  | OUTPUT INDICATORS | QUARTERLY TIMESCHEDULE |  |  |  |  |  |  |  |  |  |  |  |  | INDICATIVE BUDGET GHS |  |  |  |  |  |  |  |  |  |  | IMPLEMENTING AGENCIES |  |  |  |
|  |  |  |  |  |  |  | Q1 |  | Q2 |  | Q3 |  |  |  | Q4 |  |  |  |  | DACF |  |  | IGF |  |  | DON OR |  |  |  |  | LEAD |  | COLLABORATING |  |
| SUB PROGRAMME PHYSICAL AND SPATIAL PLANNING DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Procurement of Office Supplies & Consumables | Cape coast |  |  |  | Office Supplies & Consumables Procured |  |  |  |  |  |  |  |  |  |  |  |  |  | 19,000.00 |  |  |  |  |  | _ |  |  |  |  | PPD |  | CCMA |  |
|  | Maintenance of Official Building | CCMA |  |  |  | Official Building Maintained |  |  |  |  |  |  |  |  |  |  |  |  |  | 4,565.53 |  |  |  |  |  | - |  |  |  |  | PPD |  | CCMA |  |
|  | Green Economy Activities (Maiden Maintenance) | Cape Coast |  |  |  | Green Economy Activities (Maiden Maintenance) done |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 17,000.00 |  |  | - |  |  |  |  | PPD |  | CCMA |  |
|  | Street Naming & Property Addressing System & DPAS | CCMA |  |  |  | Street Naming & Property Addressing System done |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 30,000.00 |  |  | - |  |  |  |  | PPD |  | CCMA |  |
| SOCIAL SERVICE DELIVERY EDUCATION, YOUTH AND SPORTS MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Support to Teaching & Learning Delivery (Schools & Teachers Awards Schemes & Financial Assistance) |  | Selected schools |  |  | Teaching & Learning Delivery (Schools & Teachers Awards Schemes & Financial Assistance) Supported |  |  |  |  |  |  |  |  |  |  |  |  |  | 71,575.99 |  |  | 35,000.00 |  |  |  | _ |  |  |  | GES |  | CCMA |  |
|  | Development of Youth, Sports & Culture |  | Metro-wide |  |  | Youth, Sports & Culture Developed |  |  |  |  |  |  |  |  |  |  |  |  |  | 1,000.00 |  |  | 10,000.00 |  |  |  |  |  |  |  | GES |  | CCMA |  |
|  | Rehabilitation of School Block , |  | Jubilee School |  |  | School Block Rehabilitated |  |  |  |  |  |  |  |  |  |  |  |  |  | _ |  |  | 45,292.45 |  |  |  | _ |  |  |  | GES |  | CCMA |  |
|  | Construction of ICT Centre |  | Aboom Basic School |  |  | ICT Centre constructed |  |  |  |  |  |  |  |  |  |  |  |  |  | _ |  |  | 260,000.00 |  |  |  | _ |  |  |  | GES |  | MGSP |  |
|  | Maintenance of School Buildings (Minor Repairs) |  | Selected schools |  |  | School Buildings (Minor Repairs) Maintianed |  |  |  |  |  |  |  |  |  |  |  |  |  | _ |  |  | 10,000.00 |  |  |  | _ |  |  |  | GES |  | CCMA |  |
|  | Completion of 2 storey teachers flat |  | West End |  |  | 2 storey teachers flat Completed |  |  |  |  |  |  |  |  |  |  |  |  |  | _ |  |  | 15,594.00 |  |  |  | _ |  |  |  | GES |  | CCMA |  |
|  | Construction of 1 no. 3 unit classroom block |  | Antem |  |  | 1 no. 3 unit classroom block Constructed |  |  |  |  |  |  |  |  |  |  |  |  |  | 70,631.09 |  |  | 15,000.00 |  |  |  | _ |  |  |  | GES |  | CCMA |  |
|  | Construction of 1 No. 2 unit KG Block with ancillary facilities at Jacob Wilson Sey |  | Selected schools |  |  | 1 No. 2 unit KG Block with ancillary facilities at Jacob Wilson Sey Constructed |  |  |  |  |  |  |  |  |  |  |  |  |  | 96,471.35 |  |  | _ |  |  |  | _ |  |  |  | GES |  | CCMA |  |
|  | Supply of 500 no. dual desk for Schools in Cape Coast |  | CCMA |  |  | 500 no. dual desk for Schools in Cape Coast Supplied |  |  |  |  |  |  |  |  |  |  |  |  |  | 152,439.90 |  |  |  |  |  |  | - |  |  |  | GES |  | CCMA |  |
| SUB-PROGRAMME: SOCIAL WELFARE AND COMMUNITY DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Procurement of Office Supplies & Consumables |  | Metr Metro |  |  | Office Supplies & Consumables Procured |  |  |  |  |  |  |  |  |  |  |  |  |  | 5,493.78 |  |  |  |  |  |  | _ |  |  |  | DWSCD |  | NCCE |  |
|  | Gender Empowerment & Mainstreaming |  | Metro-wide |  |  | Gender empowered & Mainstreamed |  |  |  |  |  |  |  |  |  |  |  |  |  | 2,000.00 |  |  |  |  |  |  |  | _ |  |  | DWSCD |  | NCCE |  |
|  | Child Rights Promotion & Protection |  | Metro-wide |  |  | Child Rights Promoted & Protected |  |  |  |  |  |  |  |  |  |  |  |  |  | 24,000.00 |  |  |  |  |  |  |  | _ |  |  | DWSCD |  | NCCE |  |
| NO. | ACTIVITIES (OPERATIONS) |  | LOCATION | BASELINE |  | OUTPUT INDICATORS | QUARTERLY TIMESCHEDULE |  |  |  |  |  |  |  |  |  |  |  |  | INDICATIVE BUDGET GHS |  |  |  |  |  |  |  |  |  |  | IMPLEMENTING AGENCIES |  |  |  |
|  |  |  |  |  |  |  | Q1 |  | Q2 |  |  |  | Q3 |  |  |  | Q4 |  |  | DACF |  |  | IGF |  |  |  |  | DON OR |  |  | LEAD |  | COLLABORATING |  |
|  | Combating Domestic Violence & Human Trafficking |  | Metro-wide |  |  | Combating Domestic Violence & Human Trafficking done |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2,000.00 |  |  |  |  |  |  |  | DWSCD |  | CCMA |  |
|  | Implement People with Disability Programmes and activities |  | CCMA |  |  | People with Disability Programmes and activities Implemented |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 390,000.0 |  |  |  |  | - |  |  | DWSCD |  | NCCE |  |
| SUB- PROGRAMME: HEALTH SERVICES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Evvironmental Health Activities (Burial of Paupers, Health Screenig of Food Vendors ) |  | CCMA |  |  | Evvironmental Health Activities (Burial of Paupers, Health Screenig of Food Vendors ) done |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 8,000.00 |  |  |  |  | _ |  |  | GHS |  | CCMA |  |
|  | Environmental Sanitation management |  | CCMA |  |  | Environmental Sanitation Managed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 40,000.00 |  |  |  |  | _ |  |  | GHS |  | CCMA |  |
|  | District Response Initiatives on Malaria/ Cholera |  | Metro-wide |  |  | District Response Initiatives on Malaria done |  |  |  |  |  |  |  |  |  |  |  |  |  | 17,894.00 |  |  |  |  |  |  |  | - |  |  | GHS |  | CCMA |  |
|  | Support & Implement HIV/AIDs Activities & Programmes |  | Metro-wide |  |  | Support & Implement HIV/AIDs Activities & Programmes done |  |  |  |  |  |  |  |  |  |  |  |  |  | 40,000.00 |  |  |  |  |  |  |  | - |  |  | GHS |  | CCMA |  |
|  | Community Led Total Sanitation Implementation (CLTS) |  | Metro-wide |  |  | Community Led Total Sanitation Implementation (CLTS) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 71,000.00 |  |  |  |  | - |  |  | GHS |  | CCMA |  |
|  | Cholera Response Prevention Exercise |  | Metro-wide |  |  | Cholera Response Prevention Exercise |  |  |  |  |  |  |  |  |  |  |  |  |  | 53,400.00 |  |  |  |  |  |  |  | - |  |  | GHS |  | CCMA |  |
|  | Furnishing & Procurement of Delivery Equipments for CHPs Compounds |  | Kwaprow, Efutu Mampong, Dehia &Essuekyi |  |  | Equipments for CHPs Compounds done |  |  |  |  |  |  |  |  |  |  |  |  |  | 50,000.00 |  |  |  |  |  |  |  | - |  |  | GHS |  | CCMA |  |
|  | Extension of Electricity to CHPs Compounds |  | Kwaprow,EfutuMampong, Dehia |  |  | Furnishing & Procurement of Delivery Equipments for CHPs Compounds |  |  |  |  |  |  |  |  |  |  |  |  |  | 10,000.00 |  |  |  |  |  |  |  | - |  |  | GHS |  | CCMA |  |
|  | Extension of pipe borne water to CHPs Compounds |  | Essuekyi, Dehia & Brofoyedur |  |  | Extension of Electricity to CHPs Compounds |  |  |  |  |  |  |  |  |  |  |  |  |  | 26,000.00 |  |  |  |  |  |  |  | - |  |  | GHS |  | CCMA |  |
|  | Completion of Mpeasem CHPs Compound |  | Mpeasem |  |  | Extension of pipe borne water to CHPs Compounds |  |  |  |  |  |  |  |  |  |  |  |  |  | 30,000.00 |  |  | 4,000.00 |  |  |  |  | - |  |  | GHS |  | CCMA |  |
|  | Completion of Dankwakrom CHPs Compound |  | Dankwakrom |  |  | Completion of Dankwakrom CHPs Compound |  |  |  |  |  |  |  |  |  |  |  |  |  | 100,000.00 |  |  |  |  |  |  |  | - |  |  | GHS |  | CCMA |  |
|  | Procurement of Polytanks and Veronica Buckets and its accessories |  | CCMA |  |  | Polytanks and Veronica Buckets and its accessories procured |  |  |  |  |  |  |  |  |  |  |  |  |  | 71,990.00 |  |  |  |  |  |  |  | - |  |  | GHS |  | CCMA |  |
| NO. | ACTIVITIES (OPERATIONS) |  | LOCATION | BASELINE |  | OUTPUT INDICATORS | QUARTERLY TIMESCHEDULE |  |  |  |  |  |  |  |  |  |  |  |  | INDICATIVE BUDGET GHS |  |  |  |  |  |  |  |  |  |  | IMPLEMENTING AGENCIES |  |  |  |
|  |  |  |  |  |  |  | Q1 |  | Q2 |  |  |  | Q3 |  |  |  | Q4 |  |  | DACF |  |  | IGF |  |  |  |  | DON OR |  |  | LEAD |  | COLLABORATING |  |
|  | Repair and Maintenance of Sanitary appliance of the isolation centre at the Cape Coast Midwifery/Nursing School Hostel Building. |  | CapeCoastMidwifery/Nursing School |  |  | The isolation centre at the Cape Coast Midwifery/Nursing School Hostel Building repaired |  |  |  |  |  |  |  |  |  |  |  |  |  | 34,290.00 |  |  |  |  |  |  |  | - |  |  | GHS |  | CCMA |  |
| SUB PROGRAMME: AGRICULTURAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Improve Production Efficiency & Yield |  | Selected areas |  |  | Production Efficiency & Yield improved |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 11,400.00 |  |  |  | - |  |  |  | Dept of Agric |  | Dept. of Agric Eng, UCC. |  |
|  | Procurement of Office Supplies & Consumables |  | CCMA |  |  | Office Supplies & Consumables Procured |  |  |  |  |  |  |  |  |  |  |  |  |  | 9,000.00 |  |  |  |  |  |  | - |  |  |  | Dept. of Agric |  | Crop sci. dept. UCC |  |
|  | Manpower & Skills Development |  | CCMA |  |  | Manpower & Skills Developed |  |  |  |  |  |  |  |  |  |  |  |  |  | 6,000.00 |  |  |  |  |  |  | - |  |  |  | Dept. of Agric |  | SRID |  |
|  | Organization of Farmers Day |  | Metro wide |  |  | Farmers Day Organised |  |  |  |  |  |  |  |  |  |  |  |  |  | 6,000.00 |  |  |  |  |  |  | - |  |  |  | Dept of Agric |  | Cooperatives |  |
|  | Production & Acquisition of Improved Inputs & Seedlings |  | CCMA |  |  | Production & Acquisition of Improved Inputs & Seedlings acquired |  |  |  |  |  |  |  |  |  |  |  |  |  | 60,000.00 |  |  |  |  |  |  | - |  |  |  | Dept of Agric |  | Cooperatives |  |
|  | Undertake modernization of agriculture in Ghana programme |  | Metro wide |  |  | modernization of agriculture in Ghana programme undertaken |  |  |  |  |  |  |  |  |  |  |  |  |  | 134,037.00 |  |  |  |  |  |  | - |  |  |  | Dept of Agric |  | Cooperatives |  |
| DEVELOPMENT OF TRADE AND INDUSTRIES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Provision for payment on rehabilitation of uncompleted GRATIS Foundation Building ( Outstanding Balance) |  | CCMA |  |  | rehabilitation of uncompleted GRATIS Foundation Building ( Outstanding Balance) paid |  |  |  |  |  |  |  |  |  |  |  |  | 88,599.41 |  |  |  |  |  |  |  | - |  |  |  | CCMA |  | NBSSI |  |
|  | Provision for part payment for 10 Acres of Land for construction of warehouse and Market at Efutu |  | Efutu |  |  | 10 Acres of Land for construction of warehouse and Market paid |  |  |  |  |  |  |  |  |  |  |  |  | 100,000.00 |  |  |  |  |  |  |  | - |  |  |  | CCMA |  | NBSSI |  |
|  | Completion of Market Project |  | Efutu |  |  | Market Project Completed |  |  |  |  |  |  |  |  |  |  |  |  | 78,797.53 |  |  |  |  |  |  |  | - |  |  |  | CCMA |  | NBSSI |  |
|  | Electrification & Maintenance of Street lights in the Metropolis |  | Metro-wide |  |  | Electrification & Maintenance of Street lights in the Metropolis |  |  |  |  |  |  |  |  |  |  |  |  | 220,000.00 |  |  |  | 190,000.00 |  |  |  |  |  |  |  | CCMA |  | NBSSI |  |
|  | Support towards the training of Youth in Employable Skills |  | Metro-wide |  |  | Support towards the training of Youth in Employable Skills |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 5,000.00 |  |  |  |  |  |  |  | CCMA |  | NBSSI |  |
|  | Construction of 1NO. Mechanised Borehole with overhead tank and 4NO. Standpipe (8,000) at Abura Market |  | Abura |  |  | Construction of 1NO. Mechanised Borehole with overhead tank and 4NO. Standpipe (8,000) at Abura Market |  |  |  |  |  |  |  |  |  |  |  |  | 30,000.00 |  |  |  |  |  |  |  |  |  |  |  | CCMA |  | NBSSI |  |
|  | Construction of 1NO. Mechanised Borehole with overhead tank and 4NO. Standpipe (8,000) at Ntsin Market |  | Ntsin |  |  | Construction of 1NO. Mechanised Borehole with overhead tank and 4NO. Standpipe (8,000) at Ntsin Market |  |  |  |  |  |  |  |  |  |  |  |  | 30,000.00 |  |  |  |  |  |  |  |  |  |  |  | CCMA |  | NBSSI |  |
| NO. | ACTIVITIES (OPERATIONS) |  | LOCATION | BASELINE |  | OUTPUT INDICATORS | QUARTERLY TIMESCHEDULE |  |  |  |  |  |  |  |  |  |  |  | INDICATIVE BUDGET GHS |  |  |  |  |  |  |  |  |  |  |  | IMPLEMENTING AGENCIES |  |  |  |
|  |  |  |  |  |  |  | Q1 |  | Q2 |  |  |  | Q3 |  |  |  | Q4 |  | DACF |  |  |  | IGF |  |  |  | DON OR |  |  |  | LEAD |  | COLLABORATING |  |
|  | Repairs of Market in the Metropolis |  | Metro-wide |  |  | Market repaired in the Metropolis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 15,000.00 |  |  |  |  |  |  |  | CCMA |  | NBSSI |  |
| TRANSPORT DEPARTMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Sensitization & Awareness creation for key stakeholders on the mandate of transport department. |  | Metro-wide |  |  | Key stakeholders on the mandate of transport department Sensitized |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 10,000.00 |  |  |  | - |  |  |  | CCMA |  | TRANSPORT DEPT. |  |
|  | Periodic monitoring on-street parting (Road Safety Management) |  | CCMA |  |  | Periodic monitoring on-street parting (Road Safety Management) |  |  |  |  |  |  |  |  |  |  |  |  | 25,000.00 |  |  |  |  |  |  |  |  |  |  |  | CCMA |  | TRANSPORT DEPT. |  |
|  | Periodic grass-cutting on selected streets |  | CCMA |  |  | Periodic grass-cutting on selected streets |  |  |  |  |  |  |  |  |  |  |  |  | 18,000.00 |  |  |  |  |  |  |  |  |  |  |  | CCMA |  | TRANSPORT DEPT. |  |
|  | Periodic operations to phase-out unauthorized bus stops and terminals (Traffic management) |  | CCMA |  |  | Periodic operations to phase-out unauthorized bus stops and terminals (Traffic management) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 4,000.00 |  |  |  |  |  |  |  | CCMA |  | TRANSPORT DEPT. |  |
| SUB PROGRAMME 4:3 TOURISM DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Development & Promotion of Tourism |  | Metro-Wide |  |  | Tourism Developed & Promoted |  |  |  |  |  |  |  |  |  |  |  |  |  | 35,000.00 |  |  | 30,000.00 |  |  |  | _ |  |  |  | CCMA |  | GTB |  |
|  | Counterpart Funding for Cities Alliance Programme on Tourism Development & Sanitation Management |  | Cape Coast |  |  | Cities Alliance Programme on Tourism Development & Sanitation Management done |  |  |  |  |  |  |  |  |  |  |  |  |  | 25,000.00 |  |  | _ |  |  |  | _ |  |  |  | CCMA |  | Cities Alliance |  |
| PROGRAMME: ENVIRONMENTAL AND SANITATION SUB PROGRAMME:DISASTER PREVENTION AND MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Disaster Prevention and Management ( Sensitization flood & Tree felling) | Metro. Wide |  |  |  | Disaster (Fire & NADMO) Prevented and Managed |  |  |  |  |  |  |  |  |  |  |  |  |  | - |  |  | 35,000.00 |  |  |  | - |  |  |  | CCMA |  | NADMO |  |
|  | Embark on afforestation activities within the Metropolis | Metro. Wide |  |  |  | Afforestation done in the Metropolis |  |  |  |  |  |  |  |  |  |  |  |  |  | 4,000.00 |  |  |  |  |  |  |  |  |  |  | CCMA |  | NADMO |  |
| SUB PROGRAMME: ENVIRONMENTAL PROTECTION AND WASTE MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Solid Waste Management (Zoomlion & Landfill Site Management, clean- up exercise) | Cape Coast |  |  |  | Solid Waste (Zoomlion & Landfill Site Management, clean- up exercise) managed |  |  |  |  |  |  |  |  |  |  |  |  |  | 820,000.00 |  |  | 106,000.00 |  |  |  | _ |  |  |  | MEHO NADMO |  | CCMA |  |
|  | Construction of 4-Seater W/C Toilet with Urinal at the Biodiversity Centre | Bakaano |  |  |  | 4-Seater W/C Toilet with Urinal at the Biodiversity Centre constructed |  |  |  |  |  |  |  |  |  |  |  |  |  | 65,000.00 |  |  |  |  |  |  | _ |  |  |  | MEHO, EHAs |  | CCMA |  |
|  | Completion of 10-Seater W/C Toilet at OLA | Ola |  |  |  | 10-Seater W/C Toilet at OLA completed |  |  |  |  |  |  |  |  |  |  |  |  |  | 43,757.40 |  |  |  |  |  |  | _ |  |  |  | EHAs |  | CCMA |  |
|  | Completion of 1 No. 10 Seater W/C toilet and 10 unit shower | Amanful East |  |  |  | 1 No. 10 Seater W/C toilet and 10 unit shower completed |  |  |  |  |  |  |  |  |  |  |  |  |  | 82,000.00 |  |  |  |  |  |  | _ |  |  |  | EHAs, |  | CCMA |  |
|  | Removal of acquatic weeds in the Fosu Lagoon | Cape coast |  |  |  | Acquatic weeds in the Fosu Lagoon Removed |  |  |  |  |  |  |  |  |  |  |  |  |  | 30,000.00 |  |  |  |  |  |  | _ |  |  |  | CCMA |  | CCMA |  |
| NO. | ACTIVITIES (OPERATIONS) | LOCATION |  | BASELINE |  | OUTPUT INDICATORS | QUARTERLY TIME SCHEDULE |  |  |  |  |  |  |  |  |  |  |  |  | INDICATIVE BUDGET GHS |  |  |  |  |  |  |  |  |  |  | IMPLEMENTING AGENCIES |  |  |  |
|  |  |  |  |  |  |  | Q1 |  | Q2 |  | Q3 |  |  |  | Q4 |  |  |  |  | DACF |  |  | IGF |  |  |  | DON OR |  |  |  | LEAD |  | COLLABORATING |  |
|  | Drilling and Merchanisation of 10 No. Boreholes | Metro-wide |  |  |  | 10 No. Boreholes drilled and merchanised |  |  |  |  |  |  |  |  |  |  |  |  |  | 300,000.00 |  |  |  |  |  |  | _ |  |  |  | MEHO ,EHAs |  | CCMA |  |
|  | Spot Improvement (Maint. Of road to the final disposal site) | Selected communities |  |  |  | Spot (Maint. Of road to the final disposal site) improved |  |  |  |  |  |  |  |  |  |  |  |  |  | 25,440.00 |  |  |  |  |  |  | _ |  |  |  | MEHO, EHAs |  | CCMA |  |
|  | Maintenance of WMD vehicles | Metro-wide |  |  |  | WMD vehicles Maintained |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 50,000.00 |  |  |  | _ |  |  |  | MEHEHAs |  | CCMA |  |
| PROGRAMME 6: BUDGETING AND FINANCE SUB PROGRAMME 6:1 FINANCE AND AUDIT OPERATIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Internal Audit Operations | CCMA |  |  |  | Internal Audit Operations done |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 5,800.00 |  |  | _ |  |  |  |  | CCMA |  | FINANCE |  |
|  | Purchase of Value Books | CCMA |  |  |  | Value Books Purchased |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 60,000.00 |  |  |  |  |  |  |  | CCMA |  | FINANCE |  |
| SUB PROGRAMME: BUDGETING AND RATING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Preparation of 2020 - 2023 Composite Budget |  | CCMA |  |  | 2020 - 2023 Composite Budget Prepared |  |  |  |  |  |  |  |  |  |  |  |  |  | 30,000.00 |  |  | _ |  | _ |  |  |  |  |  | CCMA |  | BUDGET |  |
|  | Update Data on Rev. Items for Planning & Budgeting Purpose |  | CCMA |  |  | Data on Rev. Items for Planning & Budgeting Purpose Updated |  |  |  |  |  |  |  |  |  |  |  |  |  | 20,000.00 |  |  | 22,000.00 |  | _ |  |  |  |  |  | CCMA |  | BUDGET |  |
|  | Organization of In-service Training for Accounts Staff & Revenue Collectors on the new fee fixing resolution |  | Metro-wide |  |  | In-service Training for Accounts Staff & Revenue Collectors on the new fee fixing resolution Organized |  |  |  |  |  |  |  |  |  |  |  |  |  | _ |  |  | 5,000.00 |  | _ |  |  |  |  |  | CCMA |  | BUDGET |  |
|  | Property Valuation Exercise |  | Metro |  |  | Property Valuation Exercise done |  |  |  |  |  |  |  |  |  |  |  |  |  | _ |  |  | 65,000.00 |  | - |  |  |  |  |  | CCMA |  | BUDGET |  |
|  | Printing of 2020 Bills |  | Metro |  |  | 2020 Bills Printed |  |  |  |  |  |  |  |  |  |  |  |  |  | _ |  |  | 65,000.00 |  | - |  |  |  |  |  | CCMA |  | BUDGET |  |
| SUB PROGRAMME: REVENUE MOBILISATION AND MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Payments of Service Charge the Assembly Revenue Contractors and revenue collectors |  | CCMA |  |  | Service Charge the Assembly Revenue Contractors and revenue collectors Paid |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 384,000.00 |  |  | _ |  |  |  |  | CCMA |  |  | REVENUE |  |
|  | Creating of Revenue Collection Points at Amamoma |  | Amamoma |  |  | Revenue Collection Points created |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 25,000.00 |  |  |  |  |  |  |  | CCMA |  |  |  | REVENUE |

EHDG