CAPE COAST METROPOLITAN ASSEMBLY

COMPOSITE ANNUAL ACTION PLAN-2021

| MDA Programmes and Sub-programmes | NO. | Activities (Operations) | Location | Base line | Output Indicators | Quarterly Time schedule |  |  |  | Indicative Budget |  |  | Implementing Agencies |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 1st | 2nd | 3rd | 4th | GOG | IGF | Donor | Lead | Collaborating |
| PROGRAMME: MANAGEMENT AND ADMINISTRATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROGRAMME: MANAGEMENT AND ADMINISTRATION SUB-PROGRAMME: GENERAL ADMINISTRATION |  | Provide support to Strengthen Sub Metro Structure | CCMA |  | Funds released to strengthen Sub Metro Councils |  |  |  |  | 71,575.99 | - | - | CCMA | CENTRAL ADM |
|  |  | Provide support to organize official & National Celebrations | CCMA |  | Independence day/Farmers day celebration Held |  |  |  |  | - | 70,000.00 | - | CCMA | CENTRAL ADM |
|  |  | Procurement of Office Supplies & Consumables | CCMA |  | 15no. computers purchased 100 boxes of A4 sheets supplied |  |  |  |  | 27,881.34 | 151,400.00 | - | CCMA | CENTRAL ADM |
|  |  | Procurement of office Equipments and logistics(computer, printers, F& F) |  |  | Procurement of office Equipments and logistics(computer, printers, F& F) |  |  |  |  | 60,000.00 |  |  | CCMA | CENTRAL ADM |
|  |  | Provide support Payment of School Fees for Needy Students and other Recurrent Expenses of the Two MPs | CCMA |  | Number of Needy Students supported by the 2 MP’s |  |  |  |  | 480,000.00 | - | - | CCMA | CENTRAL ADM |
|  |  | Provide support for Community Initiative Programmes & Provision of Social Amenities for the Two MP's | CCMA |  | Number of Community Initiative Progammes supported by the Two MP's |  |  |  |  | 320,000.00 | - | _ | CCMA | CENTRAL ADM |
| SUB-PROGRAMME: GENERAL ADMINISTRATION |  | Undertake Information, Education & Communication activities (Adverts, Media Coverage, NACAP etc) | CCMA |  | Information, Education & Communication activities (Adverts, Media Coverage, NACAP etc) undertaken |  |  |  |  | - | 20,000.00 | _ | CCMA | CENTRAL ADM |
|  |  | Release funds for Protocol Services | CCMA |  | Funds released for Protocol Services |  |  |  |  | - | 122,000.00 | _ | CCMA | CENTRAL ADM |
|  |  | Provide Financial support to Traditional Authorities | CCMA |  | Traditional Authorities Supported |  |  |  |  | - | 39,000.00 | - | CCMA | CENTRAL ADM |
|  |  | Computerization of Records Office | CCMA | - | Mails/letters are electronically filed. |  |  |  |  | - |  | - | CCMA | CENTRAL ADM |
|  |  | Undertake Local /International Affiliations | CCMA |  | Local/International Affiliations enhanced |  |  |  |  | - | 30,000.00 | - | CCMA | CENTRAL ADM |
| SUBPROGRAMME: PLANNING AND CO-ORDINATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUBPROGRAMME: PLANNING AND CO-ORDINATION |  | Preparation of 2022-2025 MTDP | CCMA | N/A | 2022-2025 MTDP Prepared |  |  |  |  | 85,000.00 |  |  | CCMA | Planning Unit |
|  |  | Monitoring and Evaluation of development projects | CCMA | 2 m. reports | Projects monitored and evaluated, reports prepared |  |  |  |  | 50,000.00 | - | - | CCMA | Planning Unit |
|  |  | Undertake Data collection of demographic characteristics of the Metropolis (statistics) | CCMA |  | Availability of reliable and accurate Data Base |  |  |  |  | 3,000.00 |  |  | CCMA | Statistics Dept./planning Unit |
|  |  | Organize Citizens Participation programmes (Town Hall meetings, SPEEFA, Community Engagements etc) | CCMA | 3 | Over 700no. Citizens participated in Local Governance process |  |  |  |  | - | 20,000.00 | - | CCMA | CENTRAL ADM |
|  |  | Organizes MPCU Meetings | CCMA | 3 | Minutes of MPCU meeting available |  |  |  |  |  | 9,000.00 |  | CCMA | Planning Unit |
|  |  | Undertake activities for the operation of the Biodiversity Centre (Board meetings, Greening etc ) | CCMA |  | Board of trustees inaugurated, and Environmental Education Centre in operation |  |  |  |  | - | 100,000.00 | - | CCMA | CENTRAL ADM |
| SUB-PROGRAMME: LEGAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUB-PROGRAMME: LEGAL |  | Organize Administrative & Technical Meetings | CCMA |  | Administrative & Technical Meetings held |  |  |  |  | - | 266,515.00 | - | CCMA | LEGAL DEPT |
|  |  | Organization of Audit Committee Meetings | CCMA |  | Audit Committee Meetings held & Reports written and shared to relevant stakeholders |  |  |  |  | - | 20,000.00 | - | CCMA | LEGAL DEPT |
|  | SUB-PROGRAMME: LEGAL |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Justice Delivery & Legal Services | CCMA |  | Justice Delivery & Legal Services |  |  |  |  | - | 20,000.00 | - | CCMA | LEGAL DEPT |
|  |  | Undertake Public Education & Sensitization on Legal Compliance and marriage registration | CCMA | N/A | Public Education & Sensitization on Legal compliance & marriage registration enhanced |  |  |  |  |  | 7,000.00 | - | CCMA | Legal dept |
| HUMAN RESOURCE MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUB-PROGRAMME: HUMAN RESOURCE MANAGEMENT |  | Manpower & Skills Development | CCMA |  | Manpower and Skills developed |  |  |  |  | - | 186,784.00 | - | CCMA | HUMAN RES. DEPT |
|  |  | Organization of Capacity Building workshop for Assembly members on Composite Budget | CCMA |  | Capacity Building workshop for Assembly members on Composite Budget organized and reports submitted to management |  |  |  |  | - | 35,000.00 | - | CCMA | HUMAN RES. DEPT |
|  |  | Procurement of Office Equipment & Logistics (Computers, Printers, F&F) | CCMA |  | Computers, Printers purchased |  |  |  |  | 6,437.00 | - | - | CCMA | HUMAN RES. DEPT |
| SUB PROGRAMME: PUBLIC WORK SERVICE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUB PROGRAMME: PUBLIC WORK DEPARTMENT |  | Rehabilitation of the Assembly's office Block | CCMA |  | Assembly's office Block Rehabilitated |  |  |  |  | 70,705.68 | - | - | CCMA | Work Dept |
|  |  | Construction of office Block for Cape Coast North Sub Metro (Phase I) | CCMA |  | Office Block for Cape Coast North Sub Metro constructed |  |  |  |  | 200,044.28 | - | - | CCMA | Work Dept |
| SUB PROGRAMME: PUBLIC WORK DEPARTMENT |  | Completion of Community centre | Kwaprow |  | Community Centre completed |  |  |  |  | 20,028.00 |  |  | CCMA | Works Dept. |
|  |  | Undertake Supervision & Regulation of Development Control | CCMA |  | Supervision & Regulation of Development Control enhanced |  |  |  |  | 42,800.00 | - |  | CCMA | Works Dept. |
|  |  | Undertake repair and Maintenance of existing Assets (this Exclude vehicles) | CCMA |  | Existing Assets of the Assembly repaired |  |  |  |  | - | 77,000.00 | - | CCMA | Work Dept |
|  |  | Assist in Community Self-Help Projects in the Metropolis | CCMA |  | Self-Help Projects in the Metropolis supported |  |  |  |  | 162,874.98 | - | - | CCMA | Work Dept |
|  |  | Completion of Abura Police Station and construction of fence wall around the post | Abura |  | Security at Abura enhanced |  |  |  |  | 150,000.00 | - | - | CCMA | Work Dept |
| SUB- PROGRAMME: URBAN ROADS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUB- PROGRAMME: URBAN ROADS |  | Manpower & Skills Development | CCMA |  | Staff skills developed |  |  |  |  | 6,000.00 | - | - | CCMA | URBAN ROADS |
|  |  | Procurement of Office Equipment & Logistics | CCMA |  | Office Equipment & Logistics procured |  |  |  |  | 5,000.00 | - | - | CCMA | URBAN ROADS |
|  |  | Procurement of Office Supplies & Consumables | CCMA |  | Office Supplies & Consumables procured |  |  |  |  | 5,961.00 | - | - | CCMA | URBAN ROADS |
|  |  | Grass-cutting along some selected roads (Nkafoa, Nana Mbra V Avenue C’poly Junction- Mempeasem Barrier, Bonn street-UCC (Bakaano –West Gate), 3RD Ridge, Brimsu Road,) | Metropolis |  | Grass-cutting along some selected roads has been done |  |  |  |  | 56,278.00 | - | - | CCMA | URBAN ROADS |
|  |  | Desilting of earth channel (Goil filling station near Cape Coast New Stadium, Ankaful Kokodum, Pedu Praso Lorry station, Adisadel hospital, Oguaa Technical Senior High, Success City Hostel-Amamoma, Ekon M/A Primary ‘A’ School, Akyem, Kwaprow New Site PH1& PH 2) | Metropolis |  | Earth channels desilted |  |  |  |  | 74,053.80 | - | - | CCMA | URBAN ROADS |
|  |  | Road edge and Kerb cleaning (Jukwa road -Abura Goil station to Pedu Junct., Bonn Street, 3rd Ridge road) | Metropolis |  | Road edge and Kerb cleaned |  |  |  |  | 18,563.00 | - | - | CCMA | URBAN ROADS |
|  |  | Replacement of Metal Gratings on Selected Roads Within Cape Coast Metropolis John Evans Mill Avenue - Johnson Street Junction (Kotokuraba Market) John Evans Mill Avenue - Tantri Road Junction (Kotokuraba Market) Royal Street - Garden Street Junction (NIB) Atterbury Road - Frederickborg Road Junction (Brofoyedur) Royal Street – Queens Street Junction (Abease) Coronation Street – Jerusalem Road Junction) | Metropolis |  | Metal Gratings replaced |  |  |  |  | 36,425.45 | - | - | CCMA | URBAN ROADS |
| SUB PROGRAMME: PHYSICAL AND SPATIAL PLANNING DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUB PROGRAMME: PHYSICAL & SPATIAL PLANNING DEVELOPMENT |  | Procurement of Office Supplies & Consumables | Cape Coast |  | Office Supplies & Consumables procured |  |  |  |  | 17,191.00 | - | - | PPD | CCMA |
|  |  | Support activities of Land use and Spatial Planning | CCMA |  | Activities of Land use & Spatial Planning enhanced |  |  |  |  | 2,300.00 | - | - | PPD | CCMA |
|  |  | Support to carry out Green Economy Activities in the Metropolis (Maiden Maintenance) | CCMA |  | Green Economy Activities (Maiden Maintenance) carried out |  |  |  |  | - | 10,000.00 | - | PPD | CCMA |
|  |  | Procurement of Furniture and Fittings | CCMA |  | Furniture & Fittings Procured |  |  |  |  | - | 6,000.00 | - | PPD | CCMA |
|  |  | Undertake Street Naming & Property Addressing/ DPAS Exercise | CCMA |  | Street Naming & Property Addressing/ DPAS Exercise undertaken |  |  |  |  | - | 53,350.00 | - | PPD | CCMA |
| PROGRAMME: SOCIAL SERVICE DELIVERY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| EDUCATION, YOUTH AND SPORTS MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUBPROGRAMME: EDUCATION, YOUTH AND SPORTS MANAGEMENT |  | Support to Teaching & Learning Delivery (Schools & Teachers Awards Schemes & Financial Assistance) | CCMA |  | Teaching & Learning Delivery supported. |  |  |  |  | 65,149.99 | 28,000.00 | - | GES | CCMA |
|  |  | Development of Youth, Sports & Culture | CCMA |  | Youth, Sports & Culture developed |  |  |  |  | 10,000.00 | 5,000.00 | - | GES | CCMA |
|  |  | Completion of 1NO 6 Unit Class Room Block, Computer Lab, Staff Common Room & Office, with 4 Seater W/C & Urinal | Brabedzi |  | 1NO 6-Unit Class Room Block constructed |  |  |  |  | 295,625.41 | - | - | GES | CCMA |
|  |  | Maintenance of School Buildings in the Metropolis (Minor Repairs) | Metro. Wide |  | Minor repairs on School buildings carried out |  |  |  |  | - | 20,000.00 | - | GES | CCMA |
|  |  | Construction of 1No. 3- Units KG blocks at St. Mary’s - (Phase 1) | Eyifua |  | 1No. 3- Units KG blocks at St. Mary’s- Eyifua constructed |  |  |  |  | 200,000.00 | - | - | GES | CCMA |
|  |  | Construction of 1NO 3 Unit Classroom Block at Christ Church Anglican Basic Sch. | Adisadel |  | 1No. 3- Units KG blocks constructed |  |  |  |  | - | - | 281,282.96 | GES | CCMA |
|  |  | Construction of 2 bedroom self-Detached Teachers ungalow at west end | West End |  | Construction of 2 bedroom self-Detached Teachers ungalow at west end |  |  |  |  | 48,000.00 | - | - | GES | CCMA |
|  |  | Construction of 1No. 3- Units Classroom blocks at St. Nicholas | Adisadel |  | 1No. 3- Units KG blocks constructed |  |  |  |  | 281,282.96 | - | - | GES | CCMA |
|  |  | Completion of a Dining Hall Block for Ogua Sec. Technical School | Ekon |  | Dining Hall Block at Ogua Sec. Technical School constructed |  |  |  |  | 222,629.55 | - |  | GES | CCMA |
|  |  | Supply of 1,772 NO. of Mono desk for Schools in Cape Coast | Selected schs. |  | 1,772 NO. of Mono desk supplied and distributed |  |  |  |  | - | - | 244,661.04 | GES | CCMA |
| SUB PROGRAMME: SOCIAL WELFARE & COMMUNITY DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SOCIAL WELFARE & COMMUNITY DEVELOPMENT |  | Procurement of Office Supplies & Consumables | Metro. Wide |  | Office Supplies & Consumables procured |  |  |  |  | - | 10,000.00 | - | SWCD | CCMA |
|  |  | Carry out Gender Empowerment & Mainstreaming programmes | Metro. wide |  | Gender Mainstreaming programmes undertaken |  |  |  |  | - | 10,000.00 | - | SWCD | CCMA |
|  |  | Implement Child Rights Promotion & Protection Activities | Metro. wide |  | Child Rights Promotion activities implemented |  |  |  |  | 33,000.00 | - | - | SWCD | CCMA |
|  |  | Implement activities and programmes for People living with Disability | Metro. wide |  | Disability Programmes and activities Implemented |  |  |  |  | 400,000.00 | - | - | SWCD | CCMA |
| SUB PROGRAMME: HEALTH DELIVERY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| HEALTH DELIVERY |  | Environmental Health Activities (Burial of Paupers, Health Screening of Food Vendors ) | Metro. wide |  | Environmental Health Activities (Burial of Paupers, Health Screening of Food Vendors ) |  |  |  |  | - | 4,000.00 | - | GHS/MEO | CCMA |
|  |  | Embark on Environmental Sanitation & Management | Metro. wide |  | Environmental Sanitation improved |  |  |  |  | - | 20,000.00 | - | GHS/MEO | CCMA |
|  |  | Carry out District Response Initiatives on Malaria | Metro. wide |  | District Response Initiatives on Malaria undertaken |  |  |  |  | 16,287.50 | - | - | GHS | CCMA |
|  |  | Implement Community Led Total Sanitation (CLTS Activities) | Metro. wide |  | Community Led Total Sanitation implemented (CLTS Activities) |  |  |  |  | 20,000.00 | 28,000.00 | - | GHS/MEO | CCMA |
| HEALTH DELIVERY |  | Support & Implement HIV/AIDs Activities & Programmes | Metro. wide |  | HIV/AIDs Activities & Programmes carried out |  |  |  |  | 40,000.00 | - | - | GHS | CCMA |
|  |  | Carry out Quick Cholera Response Prevention Exercise | Metro. wide |  | Cholera Response Prevention Exercise implemented |  |  |  |  | 53,400.00 |  | - | GHS | CCMA |
|  |  | Make Provision for COVID-19 Related Reliefs | Metro. wide |  | COVID-19 Related Reliefs provided |  |  |  |  | 103,575.98 | 75,000.00 | - | GHS | CCMA |
|  |  | Completion of CHPs Compound | Mpeasem |  | Mpeasem CHPs Compound completed |  |  |  |  | 86,000.00 | - | - | GHS/MWD | CCMA |
| HEALTH DELIVERY |  | Completion of CHPs Compound and procurement of Hospital equipment | Dankwakrom |  | Dankwakrom CHPs Compound completed and Hospital equipment procured |  |  |  |  | 269,635.00 | - | - | GHS/MWD | CCMA |
|  |  | Maintenance and Refurbishment of CHPs Compound | Ekon |  | Ekon CHPS Compound completed |  |  |  |  | 51,665.00 | - | - | GHS /MWD | CCMA |
|  |  | Implement Public Health Services | Metro. wide |  | Public Health Services implemented |  |  |  |  | 44,000.00 | - | - | GHS | CCMA |
| PROGRAMME: ECONOMIC DELIVERY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUBPROGRAMME: TRADE AND INDUSTRIES DEV’T |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TRADE AND INDUSTRIES DEV’T |  | Provision for final payment for 10Acres of Land acquired for construction of warehouse and Market | Efutu |  | Final payment provision made |  |  |  |  | 100,000.00 | 20,000.00 | - | NBSSI | CCMA |
|  |  | Completion of Efutu Market Project | Efutu |  | Efutu Market Project completed |  |  |  |  | 78,797.53 | - | - | NBSSI | CCMA |
|  |  | Carry out Electrification & Maintenance of Street lights in the Metropolis | Metro. wide |  | Electrification & Maintenance of Street lights in the Metropolis carried out |  |  |  |  | 150,000.00 | 140,000.00 | - | NBSSI | CCMA |
|  |  | Support towards the training of Youth in Employable Skills | CCMA |  | Training of Youth in Employable Skills supported |  |  |  |  |  | 5,000.00 | - | NBSSI | CCMA |
|  |  | Implement activities on Local Economic Development (LED) | CCMA |  | Activities on Local Ecconmic Development organized |  |  |  |  | - | - | 90,000.00 |  |  |
|  |  | Repayment of Kotokuraba Market Loans | Kotokuraba |  | Kotokuraba Market Loans repaid |  |  |  |  |  | 567,578.54 | - | NBSSI | CCMA |
| SUBPROGRAMME: AGRICULTURE DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| AGRICULTURE DEVELOPMENT |  | Undertake Data collection Exercise on crops and livestock productivity | Metro. wide |  | Data Collection exercise carried out |  |  |  |  | 5,000.00 | - | - | AGRIC DEPT | CCMA |
|  |  | Procurement of Office Supplies & Consumables | Metro. wide |  | Office Supplies & Consumables procured |  |  |  |  | 14,209.00 | - | - | AGRIC DEPT | CCMA |
|  |  | Organize Farmers Day Celebration | CCMA |  | Farmers day celebration organized |  |  |  |  | 60,000.00 | - | - | AGRIC DEPT | CCMA |
|  |  | Production & Acquisition of Improved Inputs & Seedlings | Metro. Wide |  | Improved Inputs & Seedlings acquired |  |  |  |  | 80,000.00 | - | - | AGRIC DEPT | CCMA |
|  |  | Undertake modernization of agriculture in Ghana program | Metro. Wide |  | Agriculture modernized |  |  |  |  | - | - | 90,339.00 | AGRIC DEPT | CCMA |
| SUB PROGRAMME: TOURISM DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Development & Promotion of Tourism | Metro. Wide |  | Tourism boosted |  |  |  |  | 80,000.00 | 15,000.00 | - | MPCU | CCMA |
| PROGRAMME: ENVIRONMENTAL AND SANITATION MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUBPROGRAMME: DISASTER PREVENTION AND MGT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DISASTER PREVENTION AND MGT |  | Undertake Disaster Prevention and Management Activities (Tree planting in the Metropolis) | Metro. Wide |  | Disaster minimized |  |  |  |  | 39,000.00 | - | - | FIRE DEPT & NADMO | CCMA |
| SUBPROGRAMME: ENVIRONMENTAL PROTECTION AND WASTE MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUBPROGRAMME: ENVIRONMENTAL PROTECTION AND WASTE MANAGEMENT |  | Carry out Solid Waste Management (Zoomlion & Landfill Site Management, clean- up exercise) | Metro. Wide |  | clean- up exercise carried out |  |  |  |  | 770,000.00 | 106,000.00 | _ | WASTE MD | CCMA |
|  |  | Construction of 4-Seater W/C Toilet with Urinal at the Biodiversity Centre | Bakaano |  | 4-Seater W/C Toilet with Urinal at the Biodiversity Centre constructed |  |  |  |  | 32,726.24 | _ | _ | WASTE MD | CCMA |
|  |  | Completion of 10-Seater W/C Toilet at OLA | OLA |  | 10-Seater W/C Toilet at OLA completed |  |  |  |  | 43,757.40 | - | - | WASTE MD | CCMA |
|  |  | Manage Liquid waste in the Metropolis | Metro. Wide |  | Liquid waste managed |  |  |  |  | 30,000.00 | 20,000.00 | - | WASTE MD | CCMA |
| SUBPROGRAMME: ENVIRONMENTAL PROTECTION AND WASTE MANAGEMENT |  | Construction of 2NO 14 Seater W/C toilets with water systems | Siwdu, Adisadel |  | 2NO 14 Seater W/C toilets with water systems constructed |  |  |  |  | - | - | 300,000.00 | WASTE MD | CCMA |
|  |  | Environmental education on sand winning along the coast | Coastal Communities |  | Sand winning education done |  |  |  |  | 5,000.00 |  |  | WASTE MD | CCMA |
|  |  | Construction of 1NO 20 Seater W/C toilets with water systems at Philip Quacoe Girls | Abease |  | 1NO 20 Seater W/C toilets with water systems at Philip Quacoe Girls constructed |  |  |  |  | - | _ | 220,000.00 | WASTE MD | CCMA |
|  |  | Construction of 1NO. 10 Seater W/C toiltet with water system | Amanful |  | 1NO 20 Seater W/C toilets with water systems constructed |  |  |  |  | 90,000.00 | - | - | WASTE MD | CCMA |
|  |  | Removal of aquatic weeds in the Fosu Lagoon | Bakaano |  | Aquatic weeds in the Fosu Lagoon removed |  |  |  |  | 42,587.80 | _ | _ | WASTE MD | CCMA |
|  |  | Procurement of Office Equipment & Logistics (Computers, Printers, F&F) | CCMA |  | Office Equipment & Logistics procured |  |  |  |  | 8,000.00 | _ | _ | MEHO,WMD, EHAs, | CCMA |
| SUB PROGRAMME: ENV'TAL PROTECTION AND WASTE MANAG’T |  | Procurement of Office Supplies & Consumables | CCMA |  | Office Supplies & Consumables procured |  |  |  |  | 7,000.00 | - | - | WASTE MD | CCMA |
|  |  | Maintenance of Waste Management Department vehicles | CCMA |  | Waste Management vehicles maintained |  |  |  |  | - | 25,000.00 | - | WASTE MD | CCMA |
|  |  | Maintenance of Public Toilets | Metro-wide |  | Public Toilets maintained |  |  |  |  | - | 15,000.00 | - | WASTE MD | CCMA |
| SUB PROGRAMME: FORESTRY MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUB PROGRAMME: DISASTER PREVENTION AND MANAG’T |  | Establish 2.37ha Teak Plantation | Interbetin | 2.37ha | 2.37ha Teak plantation established |  |  |  |  | 6,836.54 | _ | _ | Forestry Com | YEA |
|  |  | Organize Community sensitization program on afforestation | Ankaful, Abura |  | Communities educated on Forest related issues |  |  |  |  | 2,000.00 | _ | _ | Forestry Com. | Traditional Authorities |
| PROGRAMME: BUDGETING AND FINANCE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUB PROGRAMME: FINANCE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUB PROGRAMME: FINANCE |  | Organize Internal Audit Operations | CCMA |  | Internal Audit Operations done |  |  |  |  | 25,000.00 | 15,000.00 | _ | CCMA | FINANCE |
|  |  | Purchase of Value Books | CCMA |  | Value Books Purchased |  |  |  |  | _ | 60,000.00 | _ | CCMA | FINANCE |
|  |  | Upgrade of Accounting Software | CCMA |  | Accounting software upgraded |  |  |  |  | 10,000.00 | 10,000.00 |  | CCMA | FINANCE |
| SUB PROGRAMME: BUDGET & RATING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUB PROGRAMME: BUDGET & RATING |  | Preparation of 2022 - 2025 Composite Budget | CCMA |  | 2022- 2025 Composite Budget Prepared |  |  |  |  | 30,000.00 | 15,000.00 | _ | CCMA | BUDGET & RATING |
|  |  | Update Data on Revenue Items for Planning & Budgeting Purpose | CCMA |  | Data on Rev. Items for Planning & Budgeting Purpose Updated |  |  |  |  | - | 19,000.00 | _ | CCMA | BUDGET & RATING |
|  |  | Organize In-service Training for Accounts Staff & Revenue Collectors on the Budget and the new fee fixing resolution | Metro-wide |  | In-service Training for Accounts Staff & Revenue Collectors on the new fee fixing resolution Organized |  |  |  |  | 20,000.00 | 10,000.00 | _ | CCMA | BUDGET & RATING |
|  |  | Printing of 2021 Bills | Metro-wide |  | 2020 Bills Printed |  |  |  |  | _ | 35,000.00 | - | CCMA | BUDGET & RATING |
| REVENUE MOB. MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUB PROGRAMME: BUDGETING AND RATING |  | Payments of Service Charge to the Assembly Revenue Contractors and revenue collectors | CCMA |  | Service charged paid |  |  |  |  | - | 209,488.63 | - | CCMA | BUDGET & RATING |
|  |  | Acquisition of Vehicle for Revenue Mobilization | CCMA |  | Vehicle for Revenue Mobilization acquired |  |  |  |  | - | 160,000.00 | - | CCMA | BUDGET & RATING |