CAPE COAST METROPOLITAN ASSEMBLY

COMPOSITE ANNUAL ACTION PLAN-2021(REVISED)

| MDA Programmes and Sub-programmes | NO. | Activities (Operations) | Location | B’ line | Output Indicators | Quarterly Time schedule |  |  |  | Indicative Budget |  |  | Implementing Agencies |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 1 s t | 2 n d | 3 r d | 4 t h | GOG | IGF | Donor | Lead | Collaborating |
| PROGRAMME: MANAGEMENT AND ADMINISTRATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROGRAMME: MANAGEMENT AND ADMINISTRATION SUB-PROGRAMME: GENERAL ADMINISTRATION |  | Provide support to Strengthen Sub Metro Councils | CCMA |  | Funds released to strengthen Sub Metro Councils |  |  |  |  | 90,478.00. | 50,400.00 | - | CCMA | CENTRAL ADM |
|  |  | Provide support to organize official & National Celebrations | CCMA |  | Independence Day/Farmers Day celebration Held |  |  |  |  | 90,750.00 | 68,000.00 | - | CCMA | CENTRAL ADM |
|  |  | Procurement of Office Supplies & Consumables | CCMA |  | 15no. computers purchased 100 boxes of A4 sheets supplied |  |  |  |  | 106,000.00 | 110,573.00 | - | CCMA | CENTRAL ADM |
|  |  | Procurement of Office Equipment & Logistics (Computers, Printers, F&F) | CCMA |  | Office equipment and logistics purchased |  |  |  |  | 93,000.00 | 34,068.00 |  | CCMA | CENTRAL ADM |
|  |  | Provide support Payment of School Fees for Needy Students and other Recurrent Expenses of the Two MPs | CCMA |  | Number of Needy Students supported by the 2 MP’s |  |  |  |  | 585,000.00 | - | - | CCMA | CENTRAL ADM |
|  |  | Provide support for Community Initiative Progammes & Provision of Social Amenities for the 2 MP's | CCMA |  | Number of Community Initiative Progammes supported by the Two MP's |  |  |  |  | 315,000.00 | - |  | CCMA | CENTRAL ADM |
|  |  | Release funds for Protocol Services | CCMA |  | Funds released for Protocol Services |  |  |  |  | - | 40,332.00 | _ | CCMA | CENTRAL ADM |
|  |  | Provide Financial support to Traditional Authorities | Cape Coast |  | Traditional Authorities Supported |  |  |  |  | - | 15,000.00 | - | CCMA | CENTRAL ADM |
| SUBPROGRAMME: PLANNING AND CO-ORDINATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUBPROGRAMME: PLANNING AND CO-ORDINATION |  | Undertake Local /International Affiliations activities | CCMA |  | Local/International Affiliations enhanced |  |  |  |  | - | 23,500.00 | - | CCMA | CENTRAL ADM |
|  |  | Preparation of 2022-2025 MTDP | CCMA | N/A | 2022-2025 MTDP Prepared |  |  |  |  | 64,0000 | 23,000.00 |  | CCMA | Planning Unit |
|  |  | Monitoring and Evaluation of development projects | CCMA |  | Projects monitored and evaluated; reports prepared |  |  |  |  | 145,000.00 | - | - | CCMA | Planning Unit |
|  |  | Undertake Data collection of demographic characteristics of the Metropolis (statistics) | Metro - wide |  | Availability of reliable and accurate Data Base |  |  |  |  | 3,437.00 |  |  | CCMA | Statistics Dept./planning Unit |
|  |  | Organize Citizens Participation programmes in Local Governance | CCMA | 3 | Over 700no. Citizens participated in Local Governance process |  |  |  |  | 50,000.00 | 25,000.00 | - | CCMA | CENTRAL ADM |
| SUB-PROGRAMME: LEGAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUB-PROGRAMME: LEGAL |  | Organize Administrative & Technical Meetings | CCMA |  | Administrative & Technical Meetings held |  |  |  |  | - | 94,000.00 | - | CCMA | LEGAL DEPT |
|  |  | Organization of Audit Committee Meetings | CCMA |  | Audit Committee Meetings held & Reports written and shared to relevant stakeholders |  |  |  |  | - | 12,000.00 | - | CCMA | LEGAL DEPT |
|  |  | Justice Delivery & Legal Services | CCMA |  | Justice Delivery & Legal Services |  |  |  |  | 165,000.00 | 105,000.00 | - | CCMA | LEGAL DEPT |
| HUMAN RESOURCE MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUB-PROGRAMME: HUMAN RESOURCE MANAGEMENT |  | Manpower & Skills Development | CCMA |  | Manpower and Skills developed |  |  |  |  | 95,859.00 | 69,844.00 |  | CCMA | HUMAN RES. DEPT |
|  |  | Organization of Capacity Building workshop for Assembly members on Composite Budget | CCMA |  | Capacity Building workshop for Assembly members on Composite Budget organized and reports submitted to management |  |  |  |  | - | 55,000.00 | - | CCMA | HUMAN RES. DEPT |
|  |  | Procurement of Office Equipment & Logistics (Computers, Printers, F&F) | CCMA |  | Computers, Printers purchased |  |  |  |  | 6,437.00 | - | - | CCMA | HUMAN RES. DEPT |
| SUB PROGRAMME: PUBLIC WORK SERVICE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUBPROGRAMME: PUBLIC WORK DEPARTMENT |  | Minor repair works of the Assembly's office Block | Cape Coast |  | Assembly's office Block Repaired |  |  |  |  | 140,000.00 | - | - | CCMA | WORKS DEPT. |
|  |  | Completion of Community Centre | Kwaprow |  | Community Centre completed |  |  |  |  | 80,026.00 |  |  | CCMA | WORKS DEPT |
| SUB PROGRAMME: PUBLIC WORK DEPARTMENT |  | Undertake Supervision & Regulation of Development Control | Metro wide |  | Supervision & Regulation of Development Control enhanced |  |  |  |  | - | 30,800.00 |  | CCMA | WORKS ////DEPT |
|  |  | Undertake repair and Maintenance of existing Assets (this Exclude vehicles) | CCMA |  | Existing Assets of the Assembly repaired |  |  |  |  | - | 100,479.00 | - | CCMA | WORKS DEPT |
|  |  | Assist in Community Self-Help Projects in the Metropolis | Metro wide |  | Self-Help Projects in the Metropolis supported |  |  |  |  | 320,000.00 | - | - | CCMA | WORKS DEPT |
|  |  | Completion of Abura Police Station | Abura |  | Security at Abura enhanced |  |  |  |  | 330,000.00 | - | - | CCMA | WORKS DEPT |
| SUB- PROGRAMME: URBAN ROADS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUB- PROGRAMME: URBAN ROADS |  | Manpower & Skills Development | CCMA |  | Staff skills developed |  |  | - | - | 2,000.00 | 3,000 | - | CCMA | URBAN ROADS |
|  |  | Road Signals | Metro wide |  | Road signals erected |  |  | - | - | - | 55,319.00 |  | CCMA | URBAN ROADS |
|  |  | Procurement of Office Equipment & Logistics | CCMA |  | Office Equipment & Logistics procured |  |  | - | - | 5,000.00 |  | - | CCMA | URBAN ROADS |
|  |  | Procurement of Office Supplies & Consumables | CCMA |  | Office Supplies & Consumables procured |  |  | - | - | 5,961.00 | - | - | CCMA | URBAN ROADS |
|  |  | Grass-cutting along some selected roads (Nkanfoa, Nana Mbra V Avenue C’poly Junction- Mempeasem Barrier, Bonn street-UCC (Bakaano –West Gate), 3RD Ridge, Brimsu Road,) | Nkanfoa, 3rd Ridge |  | Grass-cutting along some selected roads has been done |  |  | - | - | 56,278.00 | - | - | CCMA | URBAN ROADS |
|  |  | Desilting of earth channel (Goil filling station near Cape Coast New Stadium, Ankaful Kokodum, Pedu Praso Lorry station, Adisadel hospital, Oguaa Technical Senior High, Success City Hostel-Amamoma, Ekon M/A Primary ‘A’ School, Akyem, Kwaprow New Site PH1& PH 2) | Ankaful, Pedu, Adisadel, Amamoma, Ekon, Kwaporow |  | Earth channels desilted |  |  | - | - | 74,053.80 | - | - | CCMA | URBAN ROADS |
|  |  | Road edge and Kerb cleaning (Jukwa road -Abura Goil station to Pedu Junct., Bonn Street, 3rd Ridge Road) | 3rd Ridge |  | Road edge and Kerb cleaned |  |  |  | - | 18,563.00 | - | - | CCMA | URBAN ROADS |
|  |  | Replacement of Metal Gratings on Selected Roads Within Cape Coast Metropolis John Evans Mill Avenue - Johnson Street Junction (Kotokuraba Market) John Evans Mill Avenue - Tantri Road Junction (Kotokuraba Market) Royal Street - Garden Street Junction (NIB) Atterbury Road - Frederickborg Road Junction (Brofoyedur) Royal Street – Queens Street Junction (Abease) Coronation Street – Jerusalem Road Junction) | Kotokuraba, Brofoyedur, Abease |  | Metal Gratings replaced |  |  |  | - | 36,425.45 | - | - | CCMA | URBAN ROADS |
| SUB PROGRAMME: PHYSICAL AND SPATIAL PLANNING DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUB PROGRAMME: PHYSICAL & SPATIAL PLANNING DEVELOPMENT |  | Procurement of Office Supplies & Consumables | CCMA |  | Office Supplies & Consumables procured |  |  |  |  | 14,075.00 | - | - | PPD | CCMA |
|  |  | Support activities of Land use and Spatial Planning | CCMA |  | Activities of Land use & Spatial Planning enhanced |  |  |  |  | 2,300.00 | - | - | PPD | CCMA |
|  |  | Support to carry out Green Economy Activities in the Metropolis (Maiden Maintenance) | Metro wide |  | Green Economy Activities (Maiden Maintenance) carried out |  |  |  |  | - | 5,000.00 | - | PPD | CCMA |
|  |  | Undertake Street Naming & Property Addressing/ DPAS Exercise | Metro wide |  | Street Naming & Property Addressing/ DPAS Exercise undertaken |  |  |  |  | - | 80,000.00 | - | PPD | CCMA |
| PROGRAMME: SOCIAL SERVICE DELIVERY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| EDUCATION, YOUTH AND SPORTS MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUBPROGRAMME: EDUCATION, YOUTH AND SPORTS MANAGEMENT |  | Support to Teaching & Learning Delivery (Schools & Teachers Awards Schemes & Financial Assistance) | CCMA |  | Teaching & Learning Delivery supported. |  |  |  |  | 45,184.00 | 25,000.00 | - | GES | CCMA |
|  |  | Development of Youth, Sports & Culture | CCMA |  | Youth, Sports & Culture developed |  |  |  |  | 25,000.00 | 4,000.00 | - | GES | CCMA |
|  |  | Maintenance of School Buildings in the Metropolis (Minor Repairs) | Metro. Wide |  | Minor repairs on School buildings carried out |  |  |  |  | - | 10,000.00 | - | GES | CCMA |
|  |  | Construction of 1NO 3 Unit Class Room Block | Brabedze |  | 1NO 3-Unit Class Room Block constructed |  |  |  |  | 426,027.00 | - | - | GES | CCMA |
|  |  | Supply of 1,780 NO. of Mono desk for Schools in Cape Coast | Selected schools |  | 1,780 NO. of Mono desks supplied and distributed |  |  |  |  | 346,392.04 | - | - | GES | CCMA |
|  |  | Construction of 2 Storey 4-bedroom official accommodation For Metro Director | 3rd Ridge |  | Storey 4-bedroom official accommodation For Metro Director constructed |  |  |  |  | 517,921.00 | - | - | GES | CCMA |
| SUB PROGRAMME: SOCIAL WELFARE & COMMUNITY DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Carry out Gender Empowerment & Mainstreaming programmes |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Conduct SERs on Five (5) Victims /Issues of Domestic Violence, Missing Children and Child/ Human Trafficking | Brofoyedur, Gyegyano,Sewin, Bakano, Esuekyir, Emisaekyir, Gyegyem, Ankaful, Enyiwtsiwdo |  | SERs on Five (5) Victims/Issues of Domestic Violence, Missing Children and Child/ Human Trafficking Conducted |  |  |  |  | 500.00 | 500.00 | - | SWCD | CCMA |
|  |  | Undertake Two (2) Media Engagement Programmes |  |  | Two (2) Media Engagement Programmes Undertaken |  |  |  |  | 200.00 | 200.00 | - | SWCD | CCMA |
|  |  | Mentorship Programme for Twenty (20) Adolescents |  |  | Mentorship Programme for Twenty (20) Adolescents Conducted |  |  |  |  | 1000.00 | 1,200.00 | - | SWCD | CCMA |
|  | Implement Child Rights Promotion & Protection Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Conduct Twenty-five (25) Social Enquiries & Reporting (SERS) & Family Tracing & Reunification | Brofoyedur, Gyegyano,Sewin, Bakano, Esuekyir, Emisaekyir,Gyegyem, Ankaful,Enyiwtsiwdo |  | Twenty-five (25) Social Enquiries & Reporting (SERS) & Family Tracing & Reunification Conducted |  |  |  |  | 1,800.00 | 1,500.00 | - | SWCD | CCMA |
|  |  | Undertake 250 Child Protection Caseworks& Family Welfare Settlements & Managements (Custody, Paternity, Family Reconciliation, Child Abuse, Etc) |  |  | 250 Child Protection Caseworks& Family Welfare Settlements & Managements (Custody, Paternity, Family Reconciliation, Child Abuse, ) Undertaken |  |  |  |  | 1,000.00 | 1,000.00 |  | SWCD | CCMA |
|  |  | Undertake Sensitization & Awareness Creation and Celebration of International Days (Child Labour/Human Trafficking/Aged/ Adolescents) |  |  | Sensitization & Awareness Creation and Celebration of International Days (Child Labour/Human Trafficking/Aged/ Adolescents) Undertaken |  |  |  |  | 1,400.00 | 2,000.00 |  | SWCD | CCMA |
|  |  | Facilitate Combating Domestic Violence &Child / Human Trafficking |  |  | Combating Domestic Violence &Child / Human Trafficking facilitated |  |  |  |  | 500.00 | 1,000.00 |  | SWCD | CCMA |
|  |  | Investigation, Registration and/ or Renewal of Fifty (50) Day Care Centres & RHC |  |  | Fifty (50) Day Care Centres Investigated, Registered and Renewed |  |  |  |  | 500.00 | 800.00 |  | SWCD | CCMA |
|  |  | Conduct Two (2) Monitoring Inspections in Fifty (50) Early Childhood Care Dev,t Centres (ECCD)/ Day Care Centres & Residential Homes for Children (RHC) |  |  | Two(2) Monitoring Inspections in Fifty (50) Early Childhood Care Dev,t Centres (ECCD)/ Day Care Centres & Residential Homes for Children (RHC) Conducted |  |  |  |  | 1,000.00 | 1,000.00 |  | SWCD | CCMA |
| Implement activities and Programmes for People living with Disability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Activities Relating to Support for Persons with Disabilities (PWD’s), Destitute and NHIS Referrals | Brofoyedur, Gyegyano,Sewin, Bakano, Esuekyir, Emisaekyir,Gyegyem, Ankaful,Enyiwtsiwdo |  | Activities Relating to Support for Persons with Disabilities (PWD’s) Destitute NHIS Referrals carried out |  |  |  |  | 19,900.00 | 2,000.00 | - | SWCD | CCMA |
| UNICEF -Child Rights & Protection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Community Entry for Twenty-Five (25) communities | Brofoyedur, Gyegyano,Sewin, Bakano, Esuekyir, Emisaekyir,Gyegyem, Ankaful,Enyiwtsiwdo |  | Community Entry for Twenty-Five (25) communities conducted |  |  |  |  | - | - | 5,000.00 | SWCD | CCMA |
|  |  | Community Mobilisation & Awareness Creation/ Sensitisation |  |  | Community Mobilisation & Awareness Creation/ Sensitisation |  |  |  |  | - | - | 40,000.00 | SWCD | CCMA |
|  |  | Monitoring and Follow Up Visits |  |  | Monitoring and Follow Up Visits Conducted |  |  |  |  | - | - | 5,000.00 | SWCD | CCMA |
|  |  | Formation and Training of Community Child Protection Committees (CCPCs) |  |  | Formation and Training of Community Child Protection Committees (CCPCs) done |  |  |  |  | - | - | 13,000.00 | SWCD | CCMA |
|  |  | Inter – Sectorial Stakeholders Meetings /Engagements |  |  | Inter – Sectorial Stakeholders Meetings /Engagements held |  |  |  |  | - | - | 7,000.00 | SWCD | CCMA |
| SUB PROGRAMME: HEALTH DELIVERY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| HEALTH DELIVERY |  | Environmental Health Activities (Burial of Paupers, Health Screening of Food Vendors) | Metro. Wide |  | Environmental Health Activities (Burial of Paupers, Health Screening of Food Vendors) implemented |  |  |  |  | - | 15,000.00 | - | GHS/ MEHO | CCMA |
|  |  | Implement Urban Sanitation Project | Metro.wide |  | Urban Sanitation Project Implemented |  |  |  |  | - | - | 120,000.00 | GHS/ MEHO | CCMA |
|  |  | Embark on Environmental Sanitation & Management | Metro. Wide |  | Environmental Sanitation improved |  |  |  |  | - | 15,000.00 | - | GHS/ MEHO | CCMA |
|  |  | Carry out District Response Initiatives on Malaria | Metro. Wide |  | District Response Initiatives on Malaria undertaken |  |  |  |  | 25,000.00 | - | - | GHS | CCMA |
|  |  | Implement Community Led Total Sanitation (CLTS Activities) | Metro. Wide |  | Community Led Total Sanitation implemented (CLTS Activities) |  |  |  |  | 25,512.00 | 10,000.00 | - | GHS/ MEHO | CCMA |
| HEALTH DELIVERY |  | Support & Implement HIV/AIDs Activities & Programmes | Metro. Wide |  | HIV/AIDs Activities & Programmes carried out |  |  |  |  | 25,000.00 | - | - | GHS | CCMA |
|  |  | Carry out Quick Cholera Response Prevention Exercise | Metro. Wide |  | Cholera Response Prevention Exercise implemented |  |  |  |  | 37,800.00 | - | - | GHS | CCMA |
|  |  | Make Provision for COVID-19 Related Reliefs | Metro. Wide |  | COVID-19 Related Reliefs provided |  |  |  |  | 80,000.00 | 41,709.00 | - | GHS | CCMA |
|  |  | Implement Public Health Services | Metro. Wide |  | Public Health Services implemented |  |  |  |  | 46,000.00 | - | - | GHS | CCMA |
| PROGRAMME: ECONOMIC DELIVERY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUBPROGRAMME: TRADE AND INDUSTRIES DEV’T |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TRADE AND INDUSTRIES DEV’T |  | Provision for final payment for 10Acres of Land acquired for construction of warehouse and Market | Efutu |  | Final payment provision made |  |  |  |  | 250,000.00 | 20,000.00 | - | NBSSI | CCMA |
|  |  | Carry out Electrification & Maintenance of Street lights in the Metropolis | Metro. Wide |  | Electrification & Maintenance of Street lights in the Metropolis carried out |  |  |  |  | 250,000.00 | 140,000.00 | - | NBSSI | CCMA |
|  |  | Support towards the training of Youth in Employable Skills-(Training of 30 Male/Females in Soap Making | Cape Coast |  | Training of Youth in Employable Skills supported |  |  |  |  | - | 42,000.00 | - | NBSSI | CCMA |
|  |  | Support towards the training of Youth in Employable Skills (Training of 30 Male/Females in Block molding) | Cape Coast |  | Training of Youth in Employable Skills supported |  |  |  |  | - | 47,000.00 | - | NBSSI | CCMA |
|  |  | Support towards the training of Youth in Employable Skills- (Training of 30 Male/Females in Biodigester) | Cape Coast |  | Training of Youth in Employable Skills supported |  |  |  |  | - | 52,000.00 | - | NBSSI | CCMA |
|  |  | Maintenance of New Kotokuraba Market | Kotokuraba |  | Kotokuraba |  |  |  |  | - | 79,578.68 |  |  | CCMA |
| SUBPROGRAMME: AGRICULTURE DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| AGRICULTURE DEVELOPMENT |  | Undertake Data collection Exercise on crops and livestock productivity | Metro. Wide |  | Data Collection exercise carried out |  |  |  |  | 5,000.00 | - | - | AGRIC DEPT. | CCMA |
|  |  | Procurement of Office Supplies & Consumables | Cape Coast |  | Office Supplies & Consumables procured |  |  |  |  | 14,209.00 | - | - | AGRIC DEPT | CCMA |
|  |  | Organize Farmers Day Celebration | CCMA |  | Farmers day celebration organized |  |  |  |  | 60,000.00 | - | - | AGRIC DEPT | CCMA |
|  |  | Production & Acquisition of Improved Inputs & Seedlings | Metro. Wide |  | Improved Inputs & Seedlings acquired |  |  |  |  | 40,000.00 | - | - | AGRIC DEPT | CCMA |
|  |  | Undertake modernization of agriculture in Ghana program | Metro. Wide |  | Agriculture modernized |  |  |  |  | - | - | 53,786.45 | AGRIC DEPT | CCMA |
| SUB PROGRAMME: TOURISM DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Development & Promotion of Tourism- Stakeholders engagements, Committee meetings, Relocation of Artisan to Mempeasem, development of tourism access software’s etc | Metro. Wide |  | Tourism boosted |  |  |  |  | 80,000.00 | 5,000.00 | - | MPCU | CCMA |
| PROGRAMME: ENVIRONMENTAL AND SANITATION MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUBPROGRAMME: DISASTER PREVENTION AND MGT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DISASTER PREVENTION AND MGT |  | Undertake Disaster Prevention and Management Activities (Tree planting in the Metropolis) | Metro. Wide |  | Disaster minimized |  |  |  |  | - | 8,500.00 | - | FIRE DEPT & NADMO | CCMA |
| SUBPROGRAMME: ENVIRONMENTAL PROTECTION AND WASTE MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUBPROGRAMME: ENVIRONMENTAL PROTECTION AND WASTE MANAGEMENT |  | Carry out Solid Waste Management (Zoomlion & Landfill Site Management, clean- up exercise) | Metro. Wide |  | clean- up exercise carried out |  |  |  |  | 550,000.00 | 439,000.00 | _ | WASTE MD | CCMA |
|  |  | Completion of 4-Seater W/C Toilet with Urinal at the Biodiversity Centre | Bakaano |  | 4-Seater W/C Toilet with Urinal at the Biodiversity Centre constructed |  |  |  |  | 200,000.00 | _ | _ | WASTE MD | CCMA |
|  |  | Completion of 10-Seater W/C Toilet at OLA | OLA |  | 10-Seater W/C Toilet at OLA completed |  |  |  |  | 375,000.00 | - | - | WASTE MD | CCMA |
|  |  | Manage Liquid waste in the Metropolis | Metro. Wide |  | Liquid waste managed |  |  |  |  | 250,000.00 | 287,000.00 | - | WASTE MD | CCMA |
| SUBPROGRAMME: ENVIRONMENTAL PROTECTION AND WASTE MANAGEMENT |  | Data collection and analysis on solid waste management (Waste wise Cities) | Metro. Wide |  | Data collection and analysis on solid waste management (Waste wise Cities) implemented |  |  |  |  | - | 50,000.00 | 71,160.00 | WASTE MD | CCMA |
|  |  | Completion of 1NO 20-Seater W/C toilets with water systems at Philip Quacoe Girls | Abease |  | 1NO 20-Seater W/C toilets with water systems at Philip Quacoe Girls constructed |  |  |  |  | - | - | 220,000.00 | WASTE MD | CCMA |
|  |  | Completion of 1NO 6 unit W/C toilets and 6-unit shower | Amanful |  | 1NO 10-Seater W/C toilets with water systems constructed |  |  |  |  | 162,000.00 | - | - | WASTE MD | CCMA |
|  |  | Hiring of equipment for removal of aquatic weeds in the Fosu Lagoon | Bakaano |  | Aquatic weeds in the Fosu Lagoon removed |  |  |  |  | 60,343.00 | - | _ | WASTE MD | CCMA |
|  |  | Repair works at abattoir at Amoakofua | Amoakofua |  | Repair works at abattoir at Amoakofua completed |  |  |  |  | 49,000.00 | - | - | WASTE MD | CCMA |
|  |  | Procurement of Office Equipment & Logistics (Computers, Printers, F&F) | CCMA |  | Office Equipment & Logistics procured |  |  |  |  | 8,000.00 | _ | _ | MEHO,WMD, EHAs, | CCMA |
|  |  | Procurement of Office Supplies & Consumables | CCMA |  | Office Supplies & Consumables procured |  |  |  |  | 7,000.00 | - | - | WASTE MD | CCMA |
|  |  | Maintenance of Waste Management Department vehicles | CCMA |  | Waste Management vehicles maintained |  |  |  |  | - | 25,330.00 | - | WASTE MD | CCMA |
|  |  | Completion of 1NO. 10-seater W/C toilet | Duakor |  | 1NO. 10-seater W/C toilet constructed |  |  |  |  | - | 31,000.00 | - | WASTE MD | CCMA |
|  |  | Provision of Overhead Tank and Water Reservoir and Mechanisation of Borehole at Philip Quacoe | Abease |  | Ove head Tank and water reservoir provided and Borehole mechanized |  |  |  |  | - | 74,000.00 | - | WASTE MD | CCMA |
|  |  | Demolition and Construction of Septic tank at Wesley Girls | Kakumdo |  | Septic Tank Constructed |  |  |  |  | - | 88,000.00 | - | WASTE MD | CCMA |
|  |  | Environmental education on sand winning along the coast | Coastal Comm. |  | Sand winning education done |  |  |  |  | 5,000.00 | - | - | WASTE MD | CCMA |
| SUB PROGRAMME: FORESTRY MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Establish 2.37ha Teak Plantation | Interbetin |  | 2.37ha Teak plantation established |  |  |  |  | 6,836.54 | _ | _ | Forestry Com | YEA |
|  |  | Organize Community sensitization program on afforestation | Ankaful,Abura |  | Communities educated on Forest related issues |  |  |  |  | 2,000.00 | _ | _ | Forestry Com. | Traditional Auth. |
| PROGRAMME: BUDGETING AND FINANCE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUB PROGRAMME: FINANCE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUB PROGRAMME: FINANCE |  | Organize Internal Audit Operations | CCMA |  | Internal Audit Operations done |  |  |  |  | 25,000.00 | 15,000.00 | _ | CCMA | FINANCE |
|  |  | Purchase of Value Books | CCMA |  | Value Books Purchased |  |  |  |  | _ | 45,000.00 | _ | CCMA | FINANCE |
|  |  | Upgrade of Accounting Software | CCMA |  | Accounting software upgraded |  |  |  |  | 10,000.00 | 3,500.00 |  | CCMA | FINANCE |
| SUB PROGRAMME: BUDGET & RATING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUB PROGRAMME: BUDGET & RATING |  | Preparation of 2022 - 2025 Composite Budget | CCMA |  | 2022- 2025 Composite Budget Prepared |  |  |  |  | 50,000.00 | 12,000.00 | _ | CCMA | BUDGET & RATING |
|  |  | Update Data on Revenue Items for Planning & Budgeting Purpose | CCMA |  | Data on Rev. Items for Planning & Budgeting Purpose Updated |  |  |  |  | - | 15,000.00 | _ | CCMA | BUDGET & RATING |
|  |  | Organize In-service Training for Accounts Staff & Revenue Collectors on the Budget and the new fee fixing resolution | CCMA |  | In-service Training for Accounts Staff & Revenue Collectors on the new fee fixing resolution Organized |  |  |  |  | 25,000.00 | 8,000.00 | _ | CCMA | BUDGET & RATING |
|  |  | Printing of 2021 Bills | CCMA |  | 2020 Bills Printed |  |  |  |  | _ | 48,000.00 | - | CCMA | BUDGET & RATING |
| REVENUE MOB. MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUB PROGRAMME: BUDGETING AND RATING |  | Payments of Service Charge to the Assembly Revenue Contractors and revenue collectors | CCMA |  | Service charged paid |  |  |  |  | - | 38,000.00 | - | CCMA | BUDGET & RATING |
|  |  | Acquisition of Vehicle for Revenue Mobilization | CCMA |  | Vehicle for Revenue Mobilization acquired |  |  |  |  | - | 194,000 | - | CCMA | BUDGET & RATING |
|  |  | Creation of Revenue Point | Metro-wide |  | Creation of Revenue Point implemented |  |  |  |  | - | 9,000.00 |  | CCMA | BUDGET & RATING |